## Slide 1
STAKEHOLDER
MANAGEMENT
Procedures, Roles & Engagement — Team Briefing
Policy MAH-ENC-CNS-PM-POL-002 · Procedure MAH-ENC-CNS-PM-PRO-002
Notes: Good morning everyone, and thank you for joining. Today we are briefing the Projects Stakeholder Management Procedure, MAH-ENC-CNS-PM-PRO-002, issued under the Stakeholder Management Policy POL-002, together with its RACI matrix, the Stakeholder Engagement Plan template and the process map. By the end of this session everyone should know who our stakeholders are, how we prioritize them, who owns the engagement, and how and when to escalate.

## Slide 2
Agenda
01
Purpose & Policy Principles
02
Stakeholders, Categories & Analysis
03
Roles & Responsibilities
04
Process, Engagement & Meetings
05
Escalation Matrix & KPIs
06
Governance, Exceptions & Closeout
Notes: Six sections: purpose and policy principles; stakeholder categories and the Power-Interest analysis; roles and responsibilities including the RACI; the process, engagement planning and meetings; the six-level escalation matrix and KPIs; and finally governance priority, exceptions and closeout.

## Slide 3
01
Purpose & Policy Principles
Why this procedure exists and the rules that are never negotiable
Notes: Let's start with why this procedure exists and the few rules that apply on every project.

## Slide 4
01 · PURPOSE
Purpose & Objectives
This procedure sets a structured framework to identify, analyse, engage and communicate with internal and external stakeholders in every project phase — so expectations, concerns and inputs are recorded and addressed systematically.
1
Identify early
Identify all internal and external stakeholders at project start and record them in the Stakeholder Register.
2
Analyse & categorize
Assess power and interest with the Power–Interest Matrix to set each stakeholder's engagement priority.
3
Communicate & engage
Run the Engagement Plan: coordination meetings, authority follow-ups, workshops and progress updates.
4
Monitor & report
Track approvals, influence and engagement status; report monthly through KPIs and dashboards.
5
Learn & improve
Capture lessons learned at close-out and feed them into future MAH projects.
4
Notes: The procedure gives us one structured framework to identify, analyse, engage and communicate with internal and external stakeholders in design, procurement, construction, testing and handover. It follows the five principles of the policy: identify early and register; analyse power and interest; communicate through a structured engagement plan; monitor and report; and capture lessons learned at close-out.

## Slide 5
01 · NON-NEGOTIABLES
Governing Principles
Every stakeholder is in the Stakeholder Register with an owner, a category and an engagement priority.
No verbal-only commitments: every agreement is recorded in MoM, letter, transmittal or Aconex.
No commitment beyond delegated authority — escalate and obtain approval before confirming.
Governance first: stakeholder satisfaction never overrides policy, contract or statutory compliance.
Authority engagement goes through the GRO, with valid authorization letters.
No stakeholder issue is closed without evidence and sign-off by all concerned parties.
Policy deviations are exceptions only — justified, executive-approved, time-bound and recorded.
5
Notes: These seven principles are non-negotiable. Everyone is in the register with an owner and a priority. No verbal-only commitments. No commitment beyond your delegated authority. Governance comes first: satisfying a stakeholder never overrides policy, contract or law. Authority engagement goes through the GRO. Nothing is closed without evidence and sign-off. And policy deviations are exceptions only, justified and approved at executive level.

## Slide 6
02
Stakeholders, Categories & Analysis
Who our stakeholders are and how we prioritize them
Notes: Now, who our stakeholders are and how we analyse them.

## Slide 7
02 · DEFINITIONS
Stakeholder — Key Definitions
1
Stakeholder
Any internal or external party that has an impact on, or may be affected by, project activities — from MAH departments and project teams to the Client, consultants, authorities, subcontractors, community and service providers.
2
Stakeholder Register (SR) & Engagement Plan (SEP)
The SR is the controlled list of all stakeholders with influence / interest levels, communication plan and actions. The SEP sets communication frequency, expectations and engagement strategy; the SEP Owner updates and coordinates actions.
3
Power–Interest Matrix
The categorization model that sets communication priority: Manage Closely, Keep Satisfied, Keep Informed or Monitor. Also used: SMP – Stakeholder Management Plan · SM – Stakeholder Manager · NOC – No Objection Certificate.
7
Notes: A stakeholder is any internal or external party that affects, or is affected by, project activities. The Stakeholder Register is the controlled list of all of them, with their influence and interest and the actions agreed. The Stakeholder Engagement Plan defines how often and how we communicate with each one. The Power-Interest Matrix is the model that decides the communication priority.

## Slide 8
02 · CATEGORIES
Internal, External & Management Levels
1
Internal Stakeholders
• MAH management, functional departments, project teams and site staff.
• Design, planning, QA/QC, HSE, procurement, commercial and contracts.
2
External Stakeholders
• Client / Employer, PMC / consultants, authorities and utility owners.
• Subcontractors, vendors, service providers and community representatives.
3
Three Management Levels
• Project: Stakeholder Manager, Project Manager, Interface Manager.
• Program: Projects Director · Sector: VP E&C, PMO and Risk Manager.
8
Notes: Internal stakeholders are our management, departments, project teams and site staff. External stakeholders are the Client, PMC and consultants, authorities and utility owners, subcontractors, vendors, service providers and the community. Stakeholder management works at three levels: project, program under the Projects Director, and sector under the VP E&C with the PMO and Risk Manager.

## Slide 9
02 · ANALYSIS
Power–Interest Matrix & Engagement Strategy
9
KEEP SATISFIED
High power · Low interest
Targeted updates on decisions that need them
Executive management · approving authorities · utility owners
MANAGE CLOSELY
High power · High interest
Regular meetings and direct coordination
Client / Employer · PMC / Consultant · permitting authorities
MONITOR
Low power · Low interest
Minimal engagement — watch for changes
Non-critical suppliers · service providers · general public
KEEP INFORMED
Low power · High interest
Routine communication and progress updates
Subcontractors · internal departments · adjacent contractors · community
Notes: Every stakeholder is placed on the Power-Interest Matrix. High power and high interest: manage closely, with regular meetings and direct coordination. High power, low interest: keep satisfied with targeted updates. Low power, high interest: keep informed through routine communication. Low power, low interest: monitor with minimal engagement. The classification also considers internal or external, and the impact on cost, schedule, quality, safety and compliance. The matrix is reviewed periodically and whenever scope or stakeholders change.

## Slide 10
03
Roles & Responsibilities
Who owns what — from the E&C Sector down to subcontractors and the Client
Notes: Now, who owns what, from the sector level down to subcontractors and the Client.

## Slide 11
03 · ROLES
Stakeholder, Project & Interface Management
Stakeholder Manager
Leads the SMP, Stakeholder Register and Engagement Plan.
Analyses power / interest; chairs meetings; issues MoM in 48 hours.
Tracks KPIs and satisfaction; escalates critical issues.
Project Manager
Integrates stakeholder management into the PEP; allocates resources.
Approves the SMP and strategies affecting scope, cost or schedule.
Attends high-level meetings; decides on escalated issues.
Interface Manager
Coordinates interface points with departments, subcontractors, authorities.
Aligns the Interface Register with stakeholder engagement actions.
Supports communication flow; escalates unresolved conflicts.
11
Notes: The Stakeholder Manager leads the plan, the register and the engagement plan, runs the analysis, chairs the coordination meetings and issues minutes within 48 hours, tracks KPIs and escalates critical issues. The Project Manager integrates stakeholder management into the Project Execution Plan, approves the plan and allocates resources, and decides on escalated issues. The Interface Manager coordinates interface points and keeps the interface register aligned with stakeholder actions.

## Slide 12
03 · ROLES
Engineering, Planning & Contracts
Technical / Engineering Mgr
Reviews IFC drawings for stakeholder requirements and impacts.
Gives timely technical responses to stakeholder comments.
Presents design updates; closes technical actions in meetings.
Planning Engineer
Puts engagement milestones and commitments into the schedule.
Monitors stakeholder activities; reports delays and dependencies.
Updates dashboards of achieved and pending engagement targets.
Contract & Claim Manager
Identifies stakeholders linked to obligations, claims and variations.
Keeps all claim-related communication formal and traceable.
Assesses the contractual and financial impact of decisions.
12
Notes: The Technical or Engineering Manager reviews IFC drawings for stakeholder requirements and gives timely technical responses. The Planning Engineer puts engagement milestones into the schedule and reports delays and dependencies. The Contract and Claim Manager identifies stakeholders linked to claims and variations, keeps that communication formal and traceable, and assesses the contractual and financial impact.

## Slide 13
03 · ROLES
Support Functions, Partners & Client
1
Department Heads
Identify discipline stakeholders, raise emerging issues and close assigned actions.
2
QA/QC Manager
Addresses stakeholder quality concerns through NCRs and corrective actions.
3
Procurement
Aligns vendors and subcontractors on delivery, compliance and schedule.
4
Commercial Manager
Keeps commercial communication formal; assesses financial impact.
5
Government Relations (GRO)
Coordinates authority attendance and access; follows up permits and NOCs.
6
Subcontractors / Vendors
Report stakeholders in their scope, attend meetings, meet obligations.
7
Consultant / PMC
Reviews and approves the SMP; responds on time to contractor letters.
8
Client / Employer
Endorses the approach, approves key strategies, gives timely decisions.
13
Notes: Eight more parties complete the picture: department heads, QA/QC, procurement, the commercial manager, the Government Relations Officer, subcontractors and vendors, and on the external side the Consultant or PMC, who reviews and approves the plan, and the Client, who endorses the approach and gives timely decisions.

## Slide 14
03 · RELATIONS WITH OTHER PARTIES
Stakeholder Relations
STAKEHOLDER
MANAGER
Client / Employer
PMC /
Consultant
Authorities
(via GRO)
Subcontractors
& Vendors
Interface Manager
Community &
Third Parties
Project Team
14
Notes: The Stakeholder Manager sits at the centre: Client, PMC, authorities through the GRO, subcontractors and vendors, the Interface Manager, community and third parties, and our own project team. Each link needs an owner, a channel and a frequency, as defined in the engagement plan.

## Slide 15
03 · RACI
Stakeholder Management RACI Matrix
15
Activity / Process | Stake-holder Manager | Project Manager | Interface Manager | Projects Director | E.C. VP | Discipline Leads | Technical Engineer | Sub-contractor | Document Controller | QA/QC Manager | Safety Manager | Commercial Manager | Contract Engineer | Risk Manager
SECTOR LEVEL |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Establish stakeholder policy & governance framework | C | I | I | R | A | I | I | I | – | I | I | I | I | C
Approve sector stakeholder KPIs & reporting structure | R | I | I | C | A | I | I | I | – | I | I | C | I | C
Monitor engagement performance & compliance | A/R | C | I | R | A | I | I | I | I | I | I | C | I | C
BUSINESS UNIT LEVEL |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Develop & implement Stakeholder Management Plans | A/R | A/R | C | C | I | C | C | C | I | I | C | C | C | C
Conduct stakeholder coordination meetings | A/R | A/R | C | I | I | C | C | C | I | I | C | C | C | C
Review & approve registers and engagement plans | A/R | A/R | C | I | I | C | C | C | I | I | C | C | C | C
Escalate major issues to executive management | A/R | A/R | C | R | A | C | C | C | I | I | C | C | C | C
PROJECT LEVEL |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Identify internal & external stakeholders + owners | A/R | A/R | C | I | I | C | C | C | I | I | C | C | C | C
Classify & prioritize by influence and impact | A/R | A/R | C | C | I | C | C | C | I | I | C | C | C | C
Coordinate with stakeholders to resolve issues on site | A/R | A/R | C | C | I | C | A/R | A/R | I | I | C | C | C | C
Update & track issues in Issue Log / Register | A/R | A/R | C | I | I | C | C | C | I | I | C | C | C | C
Verify closure with all parties' sign-off | A/R | A/R | C | I | I | C | C | C | I | C | C | C | C | C
Capture & document lessons learned | A/R | A/R | C | I | I | C | C | C | I | I | C | C | C | C
R Responsible · A Accountable · C Consulted · I Informed · A/R Accountable & Responsible — Source: MAH-ENC-CNS-PM-TMP-002 Stakeholder Management RACI Matrix
Notes: This is the RACI matrix from template TMP-002. At sector level the VP E&C is accountable for the policy, the KPIs and performance monitoring, with the Projects Director and Stakeholder Manager responsible. At business-unit and project level, the Project Manager and the Stakeholder Manager are both accountable and responsible for plans, meetings, registers, identification, classification, tracking, closure and lessons learned, and the Projects Director takes major escalations. On site, subcontractors and the technical engineer are also accountable and responsible for resolving issues.

## Slide 16
04
Process, Engagement & Meetings
How every stakeholder issue moves from identification to verified closure
Notes: Next, the process every stakeholder issue follows, how we plan engagement, and the meetings that drive it.

## Slide 17
04 · PROCESS FLOW
Stakeholder Management Process Flow (Project Level)
Step 1
Identify &
Register
Stakeholder Manager
→
Step 2
Categorize &
Analyse
SM / Project Manager
→
Step 3
Communicate
& Coordinate
Interface Manager
→
Step 4
Resolve
Issues
Discipline Leads
→
Step 5
Verify &
Validate
Site Team / PM
→
Step 6
Close &
Report
SM / PM
The Project Manager approves each closure against evidence — approvals, MoMs, drawings, NOCs. If not approved, the issue returns to coordination. All documents are uploaded to Aconex before closure; KPIs and response times are reported to management.
Required Stakeholder Management Records (MAH-ENC-CNS-PM series)
Stakeholder Register (FRM-006)
Communication & Action Tracker (FRM-007)
Stakeholder MoM (FRM-008)
Monthly Summary Report (FRM-009)
Process Map (010) · Feedback Log (011)
Lessons Learned (012) · RACI · SEP
17
Notes: Six steps at project level: identify and register; categorize and analyse; communicate and coordinate through meetings, RFIs and authority follow-ups; resolve through technical, planning, commercial, QA/QC and HSE coordination; verify and validate; and close and report. The Project Manager approves each closure against evidence. If it is not approved, the issue goes back to coordination. These are the records every project keeps.

## Slide 18
04 · PROCESS MAP
One Process at Three Management Levels
1
Project Level
Identify and register stakeholders, assess them on the Power–Interest Matrix, coordinate through meetings, RFIs and authority follow-ups, resolve through discipline coordination, verify documents in Aconex and close with Project Manager approval.
2
Program Level
The Lead Interface Manager consolidates stakeholders affecting several projects and classifies them by program impact; the Projects Director validates; conflicts on schedule, approvals or shared assets are resolved and KPIs reported monthly.
3
Sector Level
The Lead Stakeholder Manager flags strategic, reputational or corporate risks; the Risk Manager assesses the impact on MAH's image and client relationship; the VP approves mitigation, the PMO monitors it and lessons are captured.
18
Notes: The same process runs at three levels. At project level it is the ten-step map we just saw. At program level the Lead Interface Manager consolidates stakeholders affecting several projects, the Projects Director validates the classification, and KPIs are reported monthly. At sector level the Lead Stakeholder Manager flags strategic or reputational risks, the Risk Manager assesses them, the VP approves mitigation, and the PMO monitors it until the risk is acceptable.

## Slide 19
04 · ENGAGEMENT PLANNING
Communication & Engagement Planning
1
Plan per
Stakeholder
Method, frequency, responsible person and information to share — aligned with the SR.
→
2
Choose the
Channel
Emails, meetings, workshops, transmittals, letters and awareness sessions.
→
3
Record &
Track
Every communication and feedback in the Communication & Action Tracker.
→
4
Review &
Update
At each stage change, or when stakeholder roles or needs change.
Communication Timing Rules (procedure requirement)
Internal meeting call
≥ 48 hours notice
External meeting invitation
≥ 72 hours notice
Minutes of Meeting (MoM)
≤ 48 hours after meeting
Stakeholder Register update
After every meeting
19
Notes: For each stakeholder we plan the method, frequency, responsible person and information to share; we choose the channel; we record every communication in the action tracker; and we review the plan at each stage change. The timing rules come from the procedure: 48 hours notice for internal meetings, 72 hours for external invitations through official channels, minutes within 48 hours, and the register updated after every meeting.

## Slide 20
04 · MEETINGS
Meetings & Stakeholder Register
Meeting Cadence
Kick-off
Once — introduce the framework, key stakeholders, roles and reporting
Weekly
Coordination: review issues, actions and new concerns (or bi-weekly)
Monthly
Review: engagement performance, open issues and KPI trends with Client / PMC
As needed
Special meeting for urgent issues, authority approvals or critical coordination
Stakeholder Register — Status Flow
Closed
Actions completed, evidence filed and all parties signed off.
Review
Under review: response agreed — awaiting verification.
Open
Action pending with owner and target date; escalate if overdue.
Meeting deliverables: MoM within 48 hours · updated Stakeholder Register · Action Tracker with target dates · Engagement Dashboard of critical stakeholders and approvals.
20
Notes: We hold a kick-off once, weekly or bi-weekly coordination meetings, a monthly review with management, the Client and the PMC, and special meetings for urgent issues or authority approvals. Every issue in the register moves from Open to Under Review to Closed. Each meeting produces minutes, an updated register, the action tracker and the engagement dashboard.

## Slide 21
04 · MEETING AGENDAS
What Every Stakeholder Meeting Covers
1
Internal Coordination Meeting
• Attendance, previous MoM, Register updates, new issues and dependencies.
• Design, schedule, permits / NOCs, risks, RFIs, actions and closure targets.
2
External Coordination Meeting
• Client, PMC, authorities, subcontractors: open issues and action status.
• Permits / NOCs via GRO, access, utilities, risks and upcoming submissions.
3
Communication & Follow-up
• Every issue logged by transmittal, email or MoM; owners acknowledge actions.
• Overdue items escalated to PM and PMC; approvals linked to the schedule.
21
Notes: Internal meetings cover attendance, the previous minutes, register updates, new issues, design, schedule and permit dependencies, risks and actions. External meetings with the Client, PMC, authorities and subcontractors cover open issues, permits and NOCs through the GRO, access, utilities and upcoming submissions. Every issue is logged, owners acknowledge their actions, and overdue items go to the Project Manager and PMC.

## Slide 22
05
Escalation Matrix & KPIs
Six escalation levels with response times — and how we measure engagement
Notes: Now the escalation matrix with its response times, and how we measure engagement.

## Slide 23
05 · ESCALATION MATRIX
Escalation Levels 1 – 3
1
Level 1 — Project Level
Response: 1–3 working days. Routine stakeholder issues and minor coordination conflicts, with no policy or contract breach. The Project Manager / Interface Manager engage the stakeholder, clarify scope and constraints, and record the issue in the Stakeholder Register.
2
Level 2 — Project Management Review
Response: 3–5 working days. Issue not resolved at project level, or with potential schedule or cost impact. The Project Manager and discipline leads coordinate internally (Technical, Planning, QA/QC, HSE) and issue a formal response to the stakeholder.
3
Level 3 — Contract & Commercial Review
Response: 5–7 working days. Proposed solution conflicts with MAH policy or the contract, or has financial implications. The Contract / Commercial Manager assesses the risks, advises on variations, claims or mitigation and gives a written recommendation.
23
Notes: Level 1 is the project level, one to three working days: routine issues, handled by the Project Manager or Interface Manager and recorded in the register. Level 2 is the project management review, three to five days, with internal coordination and a formal response. Level 3 is the contract and commercial review, five to seven days, when a solution conflicts with policy or contract, or has financial implications.

## Slide 24
05 · ESCALATION MATRIX
Escalation Levels 4 – 6
4
Level 4 — Program Level
Response: 7–10 working days. Multi-project impact, authority-level conflict, or high reputational or delivery risk. The Projects Director leads strategic engagement, cross-project alignment and direct negotiation with the stakeholder.
5
Level 5 — Sector / Executive
Response: As required / urgent. Non-compliant external request, critical legal, policy or reputational risk, or deadlock with an authority. Sector Head / Executive Management gives the final decision, communicates authority-to-authority and approves the strategic position.
6
Level 6 — Legal / Corporate Governance
Response: As required. Legal exposure, regulatory non-compliance or contractual dispute. Legal Counsel / Corporate Governance provide a legal opinion, formal notices or claims, and risk-containment actions.
24
Notes: Level 4 is the program level, seven to ten days, led by the Projects Director for multi-project, authority-level or high-risk issues. Level 5 is the sector or executive level, as required and urgent, for non-compliant requests, deadlocks with authorities or critical reputational risk. Level 6 is legal and corporate governance for legal exposure, regulatory non-compliance or contractual disputes.

## Slide 25
05 · MONITORING
Stakeholder Performance Indicators
≥85%
Stakeholder issues
resolved on time
100%
Stakeholder meetings
held as scheduled
100%
MoM issued within
48 hours
≥90%
Feedback actions closed
by target date
≥4 / 5
Stakeholder satisfaction
score (surveys)
Monthly
KPI dashboard & summary
report to management
25
Notes: The procedure's example target is at least 85 percent of stakeholder issues resolved on time. The other targets are proposed: all meetings held as scheduled, minutes within 48 hours, at least 90 percent of feedback actions closed by target date, a satisfaction score of four out of five, and a monthly KPI dashboard and summary report to management.

## Slide 26
06
Governance, Exceptions & Closeout
Decisions within authority, controlled deviations and lessons learned
Notes: Last section: governance priority, exceptions and closeout.

## Slide 27
06 · GOVERNANCE PRIORITY
Governance Priority & Decision Authority
Decision Authority (Governance Matrix)
Routine coordination → Stakeholder Mgr
Technical workaround → Project Manager
Contract / cost impact → Commercial Mgr
Authority / regulatory → Program Director
High risk / reputation → Sector Mgmt
Policy deviation → Executive approval
Requests are checked against policy, contract, law and HSE / quality / ethics; commitments beyond authority are escalated first.
Resolution Flow (SEP)
Engage
Assess
Respond
Escalate
Decide
Record*
*MAH never proceeds with a solution that breaches policy, contract, statutory requirements or governance — regardless of external pressure. Decisions go to the Register and Issue & Decision Log.
High-impact triggers
• Schedule delay over 30 days
• Major budget impact
• Specification or critical safety risk
• Authority or public reputation
27
Notes: Every decision stays within MAH's governance framework. Routine coordination is decided by the Stakeholder Manager, technical workarounds by the Project Manager, contract and cost impact by the Commercial Manager, authority matters by the Program Director, and high-risk or reputational matters by sector management. The resolution flow is engage, assess compliance, respond, escalate if needed, decide and record. High impact means more than 30 days delay, a major budget impact, a specification or critical safety risk, or an authority or public reputation concern.

## Slide 28
06 · EXCEPTIONS & CLOSURE
Exceptions, Lessons Learned & Our Commitment
Exceptions need a formal request: the issue, policy constraint, risks and mitigation.
Written Sector / Executive approval (plus Legal review if needed) before any deviation.
Approved deviations are limited in scope and time and set no precedent.
Awareness and collaboration sessions at key stages, recorded with the HSE and Interface teams.
Lessons learned captured for each exception and at close-out; records archived per document control.
Stakeholder satisfaction never overrides governance compliance.
“
MAH engages stakeholders early, communicates transparently and decides within authority — identified, analysed, engaged and closed with evidence.
Project Management leadership provides the support, resources and direction to apply this policy on every project — ensuring accountability, transparency and consistency.
28
Notes: Exceptions need a formal request with the issue, the policy constraint, the risks and the mitigation, and written executive approval before any deviation. Approved deviations are limited in scope and time and never set a precedent. Awareness sessions are held at key stages, and lessons learned are captured for every exception and at close-out. Stakeholder satisfaction never overrides governance compliance.

## Slide 29
Thank You
Questions & Discussion
Notes: That is the full procedure. The floor is open for questions on any role, meeting, escalation level or record. If something is missing for your project, raise it now so we can include it in the project Stakeholder Management Plan.