## Slide 1
INTERFACE MANAGEMENT
vs. STAKEHOLDER MANAGEMENT
A comparative analysis of two complementary MAH governance systems
How the Engineering & Construction Sector coordinates technical connection points and stakeholder relationships across project delivery

## Slide 2
Agenda
01
02
The core distinction
03
Scope and structure, side by side
04
Roles: shared vs. system-specific
05
06
07
Where the two systems intersect
Organizational separation
Key takeaways
Document basis

## Slide 3
01 · THE CORE DISTINCTION
Both disciplines coordinate people, but they control different risks
3
INTERFACE MANAGEMENT
Primary question
What must connect, align, or close?
Focus
Boundaries, dependencies, design integration and field coordination at physical, functional and organizational connection points.
Main risk if ignored
Clashes, handoff gaps, rework and unresolved technical dependencies between disciplines, packages or contractors.
STAKEHOLDER MANAGEMENT
Primary question
Who can affect the project, and how should we engage them?
Focus
Influence, interest and expectations of the people and parties who affect — or are affected by — the project, mapped on a Power–Interest Matrix.
Main risk if ignored
Resistance, non-response, conflicting expectations, reputational impact and policy deviation under external pressure.

## Slide 4
02 · SCOPE AND STRUCTURE
The same five dimensions, answered two different ways
4
INTERFACE MANAGEMENT
STAKEHOLDER MANAGEMENT
Unit of analysis
An interface point: where scopes, disciplines, organizations or information flows meet.
A stakeholder: any party that affects, or may be affected by, the project.
Categorization model
Flat split: Internal Interface Points vs. External Interface Points.
Power–Interest Matrix: Manage Closely, Keep Satisfied, Keep Informed, Monitor.
Core register
Interface Points Register + Interface Matrix Sheet (who interfaces with whom, on what).
Stakeholder Register + Stakeholder Engagement Plan (who matters, how much, how engaged).
Issue tracking tool
Interface Issue Log — escalated conflicts and physical/technical clashes.
Case Feedback Log — escalated conflicts, resistance and unmet expectations.
Owning role
Interface Manager, supported by discipline engineers and subcontractors.
Stakeholder Manager, supported by the Interface Manager and Department Heads.

## Slide 5
03 · ROLES COMPARISON
Interface Manager vs Stakeholder Manager
1
INTERFACE MANAGER
controls connection points
STAKEHOLDER MANAGER
controls relationships
vs
What it controls
Connection points, clashes and holding areas — where scopes, systems and work zones physically or contractually meet.
Influence, interest and expectations of the people and parties who affect — or are affected by — the project.
Key question
“Where do our works meet, and is every point resolved?”
“Who matters, what do they expect, and are they on board?”
Main tool
Interface Matrix · Interface Points Register
Power–Interest Matrix · Stakeholder Register & SEP
Typical items
Utility crossings and tie-ins, battery limits, work-zone handovers, shared laydown / holding areas.
Client, PMC, authorities, utility owners, subcontractors, community — approvals, NOCs, concerns.
Records
Interface Issue Log, MoM, RFIs, closure evidence and sign-off in Aconex.
Communication & Action Tracker, MoM, engagement dashboard, lessons learned.
Success measure
Interface points closed by target date — with evidence and all-party sign-off.
≥85% of stakeholder issues resolved on time; meetings held as scheduled.
Governing procedure
MAH-ENC-CNS-PM-PRO-001 · RACI TMP-001
MAH-ENC-CNS-PM-PRO-002 · RACI TMP-002 · SEP TMP-003
Two roles — they cannot be merged into one title: interfaces need technical and contractual control of points, clashes and holding areas; stakeholders need management of people, influence and expectations. Different skills, tools, registers and procedures (PRO-001 vs PRO-002) — combining them loses one or the other. They work side by side: the Interface Manager closes the technical point, the Stakeholder Manager secures the agreement behind it.

## Slide 6
04 · WHERE THEY INTERSECT
Two separate roles — connected, not merged
8
INTERFACE MANAGER
Controls connection points · PRO-001
– Interface Points Register
– Interface Matrix Sheet
– Design & field coordination
– Technical RFIs and clashes
STAKEHOLDER MANAGER
Controls relationships · PRO-002
– Stakeholder Register
– Power–Interest Matrix
– Engagement & communication plan
– Relationship-level conflicts
ALIGNED,
NOT MERGED
Each role keeps its own owner, register, RACI and procedure. The Interface Manager supports the Stakeholder Manager’s communication flow, and both registers are aligned after every coordination meeting.
Escalation stays separate but aligned: interface conflicts follow the PRO-001 escalation route; stakeholder disagreements follow the PRO-002 escalation matrix. Each manager owns his own log — both feed the same governance chain.

## Slide 7
05 · ORGANIZATIONAL SEPARATION
Two disciplines, two departments — not one combined role
9
INTERFACE MANAGEMENT
Department mandate
A technical / engineering function accountable for physical and design coordination across disciplines and contractors.
Core owner
Interface Manager — owns the Interface Points Register, Interface Matrix Sheet and Interface Issue Log.
Risk of merging the two
Technical coordination gets diluted by negotiation and relationship demands, slowing clash resolution and design sign-off.
STAKEHOLDER MANAGEMENT
Department mandate
A commercial function accountable for client, authority and stakeholder engagement and communication.
Core owner
Stakeholder Manager — owns the Stakeholder Register, Power–Interest Matrix and Engagement Plan.
Risk of merging the two
Stakeholder engagement gets diluted by day-to-day technical firefighting, weakening client and authority relationships.
Recommendation: keep Interface Management and Stakeholder Management as two separate departments, each with its own manager, register and RACI ownership. The Interface Manager should act only as the coordination bridge between them (see previous slide) — not as a merged role carrying both mandates.

## Slide 8
SUMMARY
Two separate roles on the same delivery risk — connected, never merged
Different roles, different owners
The Interface Manager controls connection points; the Stakeholder Manager controls relationships. Each has its own register, matrix, RACI and procedure (PRO-001 / PRO-002) — they cannot be merged into one title.
1
Aligned, not combined
The Interface Manager supports the Stakeholder Manager’s communication flow, and both registers are aligned after every coordination meeting — two accountable owners, one coordinated picture.
2
Escalate to the right depth
Route technical clashes through the 3-level interface escalation; route relationship, contractual or reputational issues onto the 6-level stakeholder matrix, up to Legal / Corporate Governance.
3
Notes: That's the full procedure. Open floor now — questions on any role, any gate, any interface we covered. If something wasn't clear or you think a step is missing for your specific project, raise it now so we can fold it into the project-specific LMP rather than finding out on site.

## Slide 9
10 · DOCUMENT BASIS
This comparison is drawn from four controlled MAH documents
12
MAH-ENC-PMO-PM-POL-001
Interface Management Policy
Rev.00 · 1 Oct 2025
MAH-ENC-CNS-PM-PRO-001
Projects Interface Management Procedure
Rev.00 · 1 Oct 2025
MAH-ENC-PMO-PM-POL-002
Stakeholder Management Policy
Rev.00 · 1 Nov 2025
MAH-ENC-CNS-PM-PRO-002
Projects Stakeholder Management Procedure
Rev.00 · 1 Nov 2025
Reference note: all four documents were checked and approved by the same governance chain — Projects Director, Head of HSE & TMO, Head of QA/QC and VP Engineering & Construction Sector — confirming this comparison rests on a single, coordinated set of controlled documents.