## Slide 1
INTERFACE
MANAGEMENT
Procedures, Roles & Coordination — Team Briefing
Policy Ref. MAH-ENC-INT-OP-POL-001 · Projects Interface Management Procedure
Notes: Good morning everyone, and thank you for joining. Today we are briefing the Projects Interface Management Procedure of the E&C Sector Operation Department, issued under the Interface Management Policy MAH-ENC-INT-OP-POL-001. By the end of this session everyone should know what an interface point is, who owns it, how we track it to closure, and when and how to escalate.

## Slide 2
Agenda
01
Purpose & Governing Principles
02
Definitions & Interface Types
03
Roles & Responsibilities
04
Process Flow, Meetings & Tools
05
Escalation, Integration & KPIs
06
Third-Party Assets, Awareness & Closeout
Notes: Six sections: the purpose and the rules we never bend; definitions and types of interfaces; roles and responsibilities including the RACI matrix; the process flow, meetings and tools; escalation, links to schedule and risk, and our KPIs; and finally third-party assets, awareness and closure. Please stop me at any time with questions.

## Slide 3
01
Purpose & Governing Principles
Why this procedure exists and the rules that are never negotiable
Notes: Let's start with why this procedure exists and the few rules that apply on every project, whatever the schedule pressure.

## Slide 4
01 · PURPOSE
Purpose & Objectives
This procedure sets the framework for identifying, classifying, managing and closing interface points across all MAH E&C projects — preventing design conflicts, construction delays and cost overruns.
1
Identify early
Identify, classify and document every interface point in the Interface Points Register.
2
Assign ownership
Give every interface a named owner, a target date and a resolution route.
3
Coordinate regularly
Hold coordination meetings, progress updates and resolution workshops.
4
Close with evidence
Track each point in a formal system until it is verified by all parties.
5
Learn and improve
Capture lessons learned and feed them into future phases and projects.
4
Notes: The procedure gives us one framework to identify, classify, manage and close interface points on every E&C project. In practice that means five things: identify early and register every interface point; give each one a named owner and target date; coordinate regularly through meetings and workshops; track every point until it is verified and closed with evidence; and capture lessons learned for the next phase and the next project.

## Slide 5
01 · NON-NEGOTIABLES
Governing Principles
No interface point exists outside the Interface Points Register — each one has an owner and a target date.
No verbal-only coordination: every decision is recorded in MoM, RFI, transmittal or Aconex.
No interface point is closed without evidence and sign-off by all concerned parties.
No issue stays unresolved beyond its target date without formal escalation.
Authority coordination goes through the GRO, with a valid Client authorization letter.
Escalation is fact-based and used when coordination fails — it never replaces coordination.
Safety-related interface issues may be escalated immediately to any level, regardless of hierarchy.
5
Notes: These seven principles are non-negotiable. Everything goes in the register with an owner and a date. Nothing is agreed verbally only. Nothing is closed without evidence and sign-off by all parties. Nothing stays overdue without formal escalation. Authority coordination goes through the GRO with a valid Client authorization letter. Escalation is fact-based and never replaces coordination. And safety-related interface issues can be escalated immediately to any level.

## Slide 6
02
Definitions & Interface Types
What an interface point is and where interfaces arise
Notes: Now some definitions, so we all use the same language, and a look at where interfaces arise.

## Slide 7
02 · DEFINITIONS
Interface Point (IP) — Definition & Types
1
Interface Point (IP)
A location, activity or information flow where two or more parties, systems or scopes meet and require coordination. The Interface Owner is the person or department assigned to manage and close it.
2
Physical · Functional · Organizational
Physical: scopes meet on site (clashes, crossings, tie-ins). Functional: systems must integrate. Organizational: a responsibility boundary between parties (battery limits).
3
Why it matters
Minimizes risk and design / construction conflicts, avoids delays and cost overruns, optimizes resources and supports timely decisions and stakeholder alignment.
7
Notes: An interface point is a location, activity or information flow where two or more parties, systems or scopes meet and need coordination. The interface owner is the person or department responsible for managing and closing it. Interfaces are physical, functional or organizational. Managing them well reduces conflicts, avoids delays and cost overruns, and supports timely decisions.

## Slide 8
02 · INTERFACE TYPES
Internal, External & Sister-Company Interfaces
1
Internal Interfaces
• Engineering ↔ Construction, Planning ↔ Procurement, QA/QC ↔ Site, HSE ↔ concurrent works.
• Design data release, shop drawings, inspections, NCRs, schedule, budget and Aconex transmittals.
2
External Interfaces
• Client, PMC / Consultant, subcontractors, vendors, authorities, utilities and adjacent contractors.
• Approvals, IFC / as-built reviews, work-area handover, permits, NOCs and final acceptance.
3
Sister-Company Interfaces
• Dedicated coordination meeting: Planning, Technical, PM, Procurement, QA/QC, HSE, Interface.
• Joint Responsibility Matrix signed by both parties; no deviation without formal re-issue.
8
Notes: Interfaces are internal, between our own departments; external, with the Client, consultant, subcontractors, authorities, utilities and adjacent contractors; and between MAH and sister companies in the group. For sister companies we hold a dedicated coordination meeting and jointly sign a Responsibility Matrix covering scope boundaries, roles, decision authority and escalation channels. Nothing deviates from it without formal re-issue.

## Slide 9
02 · PROJECT LIFE CYCLE
Interfaces Across the Project Life Cycle
1
Tender &
Design
Scope boundaries, package overlaps, discipline clashes, IFC revisions and data release.
→
2
Procurement
& Vendors
Long-lead items vs design freeze, vendor approvals and material handover points.
→
3
Construction
& Site
Work-zone handover, sequencing, site clashes and authority dependencies.
→
4
Testing &
Handover
System integration, as-builts, final approvals, NOCs and acceptance.
Communication Timing Rules (procedure requirement)
Internal meeting call
≥ 48 hours notice
External meeting invitation
≥ 72 hours notice
Minutes of Meeting (MoM)
≤ 48 hours after meeting
Interface Register update
After every meeting
9
Notes: Interfaces change through the life cycle: scope boundaries and design clashes at tender and design; long-lead items and vendor approvals at procurement; work-zone handovers, sequencing and authority dependencies during construction; and integration, as-builts and final approvals at handover. At the bottom are the communication timing rules from the procedure: 48 hours notice for internal meetings, 72 hours for external ones, minutes within 48 hours and the register updated after every meeting.

## Slide 10
03
Roles & Responsibilities
Who owns what — from the E&C Sector down to subcontractors
Notes: Now, who owns what — from the E&C Sector level down to our subcontractors.

## Slide 11
03 · ROLES
Leadership & Interface Management
Projects Director
Approves Interface Management Plans, Registers and Issue Logs.
Receives Level 2 escalations on schedule, cost, quality or safety.
Escalates critical issues to the VP E&C Sector.
Project Manager
Ensures alignment and collaboration across all project teams.
Approves resolutions with cost or schedule impact; supports escalation.
Ensures every interface decision is documented and implemented on site.
Interface Manager
Develops and maintains the Interface Register, Matrix and Issue Log.
Chairs coordination meetings; issues MoM within 48 hours; tracks RFIs.
Coordinates Client, PMC and authorities (via GRO); reports and escalates.
11
Notes: The Projects Director approves the interface plans, registers and issue logs and takes Level 2 escalations. The Project Manager ensures alignment across teams, approves resolutions with cost or schedule impact and makes sure decisions are implemented on site. The Interface Manager runs the system day to day: the register, matrix and issue log, the coordination meetings and minutes, and coordination with the Client, PMC and authorities through the GRO.

## Slide 12
03 · ROLES
Engineering & Site Execution Team
Technical / Design Manager
Reviews IFC drawings to identify interface points between trades.
Answers interface RFIs; issues integrated drawings and as-built data.
Keeps a record of all technical coordination outcomes.
Construction Manager
Coordinates field activities of disciplines working in adjacent zones.
Keeps sequences within agreed interface boundaries and dates.
Reports site clashes at once; implements and documents resolutions.
Planning Engineer
Integrates interface milestones into the master schedule and look-ahead.
Treats permits, NOCs and third-party dependencies as predecessors.
Alerts the Interface Manager early to schedule risks.
12
Notes: The Technical or Design Manager identifies interface points in the IFC drawings and answers interface RFIs. The Construction Manager coordinates disciplines working in adjacent zones, keeps sequences within the agreed boundaries and reports clashes immediately. The Planning Engineer puts interface milestones into the schedule and treats permits and third-party dependencies as predecessors.

## Slide 13
03 · ROLES
Support & Enabling Functions
1
QA/QC
Verifies interface compliance, inspects zones before handover, issues and closes NCRs.
2
HSE
Controls safety where operations overlap; delivers awareness sessions and records.
3
Surveying Team
Verifies boundaries and control points; joint surveys and as-built data for closure.
4
Procurement
Aligns deliveries with resolution plans; defines handover points in packages.
5
Commercial / Contracts
Supports VOs and claims; issues timely contractual notices.
6
Government Relations (GRO)
Liaises with MOT, Municipality, SEC, NWC, Civil Defense for permits and NOCs.
7
Subcontractors / Vendors
Attend meetings, submit shop drawings of connection points, keep to boundaries.
8
Consultant / PMC & Client
Approve resolutions and major decisions; review monthly interface reports.
13
Notes: Eight support functions make the system work: QA/QC, HSE, the survey team, procurement, commercial and contracts, the Government Relations Officer, our subcontractors and vendors, and on the external side the Consultant or PMC and the Client, who approve resolutions and major decisions.

## Slide 14
03 · RELATIONS WITH OTHER PARTIES
Interface Manager Relations
INTERFACE
MANAGER
Client / Employer
PMC /
Consultant
Authorities
(via GRO)
Subcontractors
& Vendors
Utilities
Third Parties &
Adjacent Contractors
Project Team
14
Notes: The Interface Manager sits at the centre of all these relationships: Client, PMC, authorities through the GRO, subcontractors and vendors, utilities, third parties and adjacent contractors, and our own project team. If any one of these links fails, the interface fails — which is why coordination is the job, not an extra.

## Slide 15
03 · RACI
Interface Management RACI Matrix
15
Activity / Process | Interface Manager | Project Manager | Projects Director | E.C. VP | Discipline Leads | Technical Engineer | Sub-contractor | Document Controller | QA/QC Manager | Safety Manager | Commercial Manager | Contract Engineer | Risk Manager
SECTOR LEVEL |  |  |  |  |  |  |  |  |  |  |  |  | 
Establish interface policy & governance framework | I | I | C | A | I | I | I | I | I | I | I | I | I
Approve sector interface KPIs & reporting structure | I | I | R | A | I | I | I | I | I | I | C | I | I
Monitor interface performance & compliance | C | C | R | A | I | I | I | I | I | I | I | I | I
BUSINESS UNIT LEVEL |  |  |  |  |  |  |  |  |  |  |  |  | 
Develop & implement Interface Management Plans | R | C | A | I | R | R | C | I | I | I | C | C | C
Conduct interface coordination meetings | A | C | C | I | R | R | C | I | I | I | C | C | C
Review & approve Interface Registers and Issue Logs | R | C | A | I | R | R | C | I | I | I | C | C | C
Escalate major conflicts to executive management | R | C | A/R | A | R | C | C | I | I | I | R | C | C
PROJECT LEVEL |  |  |  |  |  |  |  |  |  |  |  |  | 
Identify internal & external interface points + owners | A/R | A | C | I | R | R | R | I | I | C | I | R | C
Coordinate with stakeholders to resolve issues on site | A/R | A | I | I | R | R | A/R | I | I | C | I | R | C
Update & track issues in Interface Log and Matrix | A/R | A | I | I | C | C | C | I | C | C | I | C | C
Verify closure with all parties' sign-off | A/R | A | I | I | R | R | C | I | I | C | I | C | C
Upload final documents & closure evidence to Aconex | A/R | A | I | I | R | R | C | A/R | A/R | I | I | C | I
Capture & document lessons learned | C | A | I | I | I | C | R | I | I | C | C | R | A/R
R Responsible · A Accountable · C Consulted · I Informed · A/R Accountable & Responsible — Source: MAH-ENC-CNS-PM-TMP-001 Interface Management RACI Matrix
Notes: This is the RACI matrix from template MAH-ENC-CNS-PM-TMP-001. At sector level the VP E&C is accountable for policy, KPIs and performance monitoring. At business-unit level the Projects Director is accountable for plans, registers and escalations, with the Interface Manager accountable for coordination meetings. At project level the Project Manager is accountable and the Interface Manager is both accountable and responsible for identifying, tracking, closing and uploading evidence to Aconex. Lessons learned are owned by the Risk Manager.

## Slide 16
04
Process Flow, Meetings & Tools
How every interface point moves from identification to verified closure
Notes: Next, the process every interface point follows, the meetings that drive it, and the three tools we use.

## Slide 17
04 · PROCESS FLOW
Interface Management Process Flow
Step 1
Identify &
Classify
All parties / IM
→
Step 2
Register &
Assign Owner
Interface Manager
→
Step 3
Coordinate
Meeting / RFI
IM / Disciplines
→
Step 4
Resolve
Agreed Action
Owner / Construction
→
Step 5
Verify
Evidence
QA/QC / Survey / IM
→
Step 6
Close &
Sign-off
All parties / PM
An interface point stays open until it is verified and signed off by all concerned stakeholders. Closure evidence is filed in Aconex; points past their target date are formally escalated.
Required Interface Management Records (MAH-ENC-CNS-PM series)
Interface Points Register (FRM-001)
Interface Issue Log (FRM-002)
Interface Meeting Minutes (FRM-003)
Interface Management Process Map (FRM-004)
Interface Matrix Sheet (FRM-005)
Meeting Log (FRM-006) & RACI (TMP-001)
17
Notes: Six steps: identify and classify; register and assign an owner; coordinate through meetings or RFIs; resolve with an agreed action; verify with evidence; and close with sign-off by all concerned parties. A point stays open until it is verified and signed off, and the evidence goes into Aconex. These are the records every project must keep, from the Interface Points Register to the RACI matrix.

## Slide 18
04 · COMMUNICATION
Meetings & Interface Points Register
Meeting Cadence
Kick-off
Once — agree roles, templates, reporting and communication flow
Weekly
Coordination: review new, open and closed points; agree actions
Monthly
Interface review: closure rate and key risks with management / Client
As needed
Special meeting for urgent items affecting progress, approvals or safety
Interface Register — Status Flow
Closed
Verified and signed off by all parties; evidence in Aconex.
Review
Under review: resolution agreed — awaiting verification and sign-off.
Open
Action pending with owner and target date; escalate if overdue.
Register fields: Interface ID · description · location / zone · originator & receiver discipline · type · required action / responsibility · target date · status · remarks.
18
Solved
Finish in Interface and still not finish for construction work.
Notes: We hold a kick-off meeting once to agree roles and templates, weekly or bi-weekly coordination meetings, a monthly review with management and the Client, and special meetings for urgent items. Every point in the register moves from Open to Under Review to Closed, and these are the fields the register must contain.

## Slide 19
04 · TOOLS
Interface Management Tools
1
Interface Matrix
• Maps who interfaces with whom, on what scope and where boundaries lie.
• Built early; updated monthly or whenever scopes or packages change.
2
Interface Points Register
• Tracks every coordination point: owner, target date and status.
• Updated weekly, after every coordination meeting.
3
Interface Issue Log
• Records conflicts affecting progress, cost or safety and how they were resolved.
• Basis for contractual notices, claims and risk monitoring.
19
Notes: Three tools with three different jobs. The Interface Matrix defines where coordination is needed. The Interface Points Register tracks progress of each point week by week. And the Interface Issue Log records what happens when coordination fails, which gives us the record we need for notices, claims and risk.

## Slide 20
05
Escalation, Integration & KPIs
Time-bound escalation and how we measure interface performance
Notes: Now how we escalate, how interfaces link to schedule, risk and contract, and how we measure performance.

## Slide 21
05 · ESCALATION
Internal Escalation Mechanism
1
Level 1 — Project Level
Issue unresolved after the coordination meeting, or affecting short-term activities. Interface Manager escalates to the Project Manager — response within 2–5 working days.
2
Level 2 — Program Level
Issue impacting schedule, cost, quality or safety. Project Manager escalates to the Projects Director / Head of Interface — response within 5–8 working days.
3
Level 3 — E&C Sector
Critical issue affecting milestones, contract obligations or program objectives. Projects Director escalates to the VP E&C Sector — immediate instructions and decision.
21
Notes: Internally there are three levels. Level 1: the Interface Manager escalates to the Project Manager within 2 to 5 working days. Level 2: the Project Manager escalates to the Projects Director or Head of Interface within 5 to 8 days when schedule, cost, quality or safety is affected. Level 3: the Projects Director escalates critical issues to the VP E&C Sector for immediate decision.

## Slide 22
05 · ESCALATION
External Escalation Mechanism
1
Level 1 — Coordination Level
Routine issue: Interface Manager follows up with the Consultant / Subcontractor (3–5 working days); if progress is affected, the PM escalates to the PMC Team Leader.
2
Level 2 — Client Level
Issue impacting milestones, approvals or permits: the Project Manager escalates to the Client / Employer Representative — response within 7–14 working days.
3
Level 3 — Authority / Executive Level
Critical issue on permits, NOCs or statutory compliance: Project Director / GRO escalate to the Authority or Client senior management — immediately / as required.
22
Notes: Externally: Level 1 is coordination with the consultant or subcontractor, 3 to 5 days, and then the PMC team leader. Level 2 is the Client level for milestones, approvals and permits, 7 to 14 days. Level 3 is authority or executive level for permits, NOCs and statutory compliance, handled by the Project Director and GRO. All authority-related escalations go through the GRO and are supported by written records.

## Slide 23
05 · INTEGRATION
Links to Schedule, Risk & Contract
1
Schedule
Interface milestones sit in the master schedule and look-ahead. Permits, NOCs and third-party dependencies are predecessors of critical activities.
2
Risk
Every interface point is a potential risk or opportunity (ISO 31000). Critical interfaces are linked to the Risk Register with mitigation actions and owners.
3
Contract & Escalation Principles
Escalation is fact-based and time-bound, supported by drawings, schedules and correspondence. The Contract & Claims Manager issues timely notices to protect our rights.
23
Notes: Interface management is linked to the rest of project controls. Interface milestones are in the schedule, and permits and third-party dependencies are predecessors. Critical interfaces are in the risk register. And escalation is always fact-based, with the Contract and Claims Manager issuing timely notices to protect our rights.

## Slide 24
05 · MONITORING
Interface Performance Indicators (proposed targets)
100%
Interface points with
owner & target date
≥90%
Interface points closed
by target date
100%
MoM issued within
48 hours
100%
Closures with evidence
& sign-off in Aconex
Zero
Overdue items without
formal escalation
4 / yr
Awareness sessions
(quarterly minimum)
24
Notes: These are proposed targets to measure the system: every point has an owner and a date; at least 90 percent closed by target date; minutes within 48 hours; every closure evidenced in Aconex; zero overdue items without escalation; and at least four awareness sessions a year.

## Slide 25
06
Assets, Awareness & Closeout
Protecting what is not ours and keeping every team aligned
Notes: Last section: third-party assets, awareness, and how we close out.

## Slide 26
06 · THIRD-PARTY ASSETS
Damage to Third-Party Assets — Prevent & Respond
Third-Party Assets at Risk
Underground power & HV cables
Water, sewer & stormwater networks
Telecom & fiber-optic networks
Gas / fuel pipelines, chambers & valves
Roads, pavements & public infrastructure
Adjacent contractor & private property
Prevention: utility detection and trial pits, marking, PTW, RA/JSA, toolbox talks, certified equipment, competent operators, supervision and coordination with utility owners.
Immediate Response
Stop
Secure
Protect
Notify
Record
Resume*
*Work resumes only after written approval from Project Management. External communication (utility owners, authorities, Civil Defense, Police, media) by authorized management only.
Damage categories
• Minor or major asset damage
• Utility strike
• Environmental damage
• Public, private or critical infrastructure damage
26
Notes: Many interfaces involve assets that are not ours: cables, pipelines, networks, roads and neighbouring property. Prevention comes first — detection, trial pits, marking, permits, risk assessments and coordination with utility owners. If damage happens: stop, secure, protect, notify, record, and resume only with written approval from project management. External communication is only by authorized management, in line with the incident reporting procedure MAH-ENC-HSE-HE-PRO-008.

## Slide 27
06 · AWARENESS & CLOSURE
Awareness, Lessons Learned & Our Commitment
Quarterly awareness sessions — plus after phase changes, new subcontractors or incidents.
HSE Manager delivers sessions and records attendance; PM ensures full participation.
Avoid: verbal-only coordination, no owner or date, no follow-up, closure without evidence.
Best practice: register at once, assign an owner, update weekly, close with evidence.
Records retained for the contract period or project duration + 1 year.
No interface point is closed until it is verified, evidenced in Aconex and signed off by all parties.
“
MAH manages interfaces as an integrated project-control function — identified early, owned, tracked and closed with evidence.
Management provides the leadership, resources and guidance to apply this policy on every E&C project — minimizing risks, avoiding delays and optimizing resources.
27
Notes: Awareness sessions are held quarterly and after major changes, delivered by HSE with the Interface Manager, and the Project Manager makes sure everyone attends. Avoid the common mistakes: verbal-only coordination, no owner, no follow-up, closure without evidence. We manage interfaces as an integrated project-control function, and management provides the resources to make it work.

## Slide 28
Thank You
Questions & Discussion
Notes: That is the full procedure. The floor is open — questions on any role, meeting, escalation level or tool. If something is missing for your project, raise it now so we can include it in the project Interface Management Plan.