## Slide 1
LOGISTICS
MANAGEMENT
Procedures, Roles & Site Interfaces — Team Briefing
Doc. Ref. MAH-ENC-CNS-PM-PRO-001
Notes: Good morning everyone, and thank you for joining. Today we're briefing the Logistics Management procedure — document reference MAH-ENC-CNS-PM-PRO-001. This session covers our procedures, roles, and how the logistics team interfaces with everyone else on site. My goal is that by the end of this, everyone leaves knowing exactly what's expected of their team and who to talk to when something needs to move.

## Slide 2
Agenda
01
Purpose & Governing Principles
02
Roles & Responsibilities
03
Approval Gates & Delivery Process
04
Site Operations Control
05
Communication, KPIs & Escalation
06
Risk, Nonconformance & Closeout
Notes: Here's how we'll walk through it: first the purpose and the non-negotiable ground rules, then roles and responsibilities across the team — including how we interface with everyone else on site. After that, the approval gates and delivery process, site operations control, our communication and KPI structure, and finally risk, nonconformance and how we close a project out. Six sections, roughly three to four minutes each — stop me anytime with questions.

## Slide 3
01
Purpose & Governing Principles
Why this procedure exists and the rules that are never negotiable
Notes: Let's start with why this procedure exists and the handful of rules we never bend, no matter how much schedule pressure we're under.

## Slide 4
01 · PURPOSE
Purpose & Objectives
This procedure establishes the mandatory framework for planning, approving, coordinating, executing, monitoring and closing logistics activities across MG / E&C construction and infrastructure projects.
1
Protect performance
Safeguard project schedule, cost, quality and HSE performance.
2
Prevent disruption
Prevent congestion, double handling, idle resources and workfront disruption.
3
Maintain safe access
Maintain safe public traffic, property, pedestrian and emergency access.
4
Control interfaces
Control logistics interfaces with suppliers, subcontractors, authorities and adjacent stakeholders.
5
Every project needs a plan
Require every project to prepare a project-specific Logistics Management Plan (LMP).
4
Notes: This procedure exists to make sure materials, equipment, manpower and services get to the right workfront, at the right time, safely and through an approved route. In practice that means five things: we protect schedule, cost, quality and HSE performance; we prevent congestion and double handling; we keep public, pedestrian and emergency access safe at all times; we control our interfaces with suppliers, subcontractors and authorities; and every single project has to run its own project-specific Logistics Management Plan built on top of this corporate procedure — no project operates without one.

## Slide 5
01 · NON-NEGOTIABLES
Governing Principles
No logistics activity proceeds without an approved requirement, owner and confirmed workfront.
No mobilization before the applicable mobilization gate has been satisfied.
No live-traffic movement without TMP controls and Traffic / HSE confirmation.
No abnormal load without route verification, permits and escorts.
Materials are traceable from purchase and dispatch through receipt, storage and installation.
Any deviation is risk-assessed, approved and recorded before implementation.
Every person in logistics operations has authority to stop an unsafe or unauthorized movement.
5
Notes: These seven principles are non-negotiable — please take a moment to actually read them. No activity moves without an approved requirement and a confirmed workfront. No mobilization before its gate is satisfied. No live-traffic movement without TMP and Traffic or HSE sign-off. No abnormal load without route verification and permits. Materials must be traceable end to end. Any deviation gets risk-assessed and approved before it happens, not after. And critically — every single person on this team, regardless of position, has the authority to stop an unsafe or unauthorized movement. That last point is the one I want everyone to remember.

## Slide 6
02
Roles & Responsibilities
Who owns what across leadership, site execution and support functions
Notes: Now the part most of you are here for: who owns what. We'll go through leadership, site execution, and every support function we depend on — then look at how logistics ties into all of them.

## Slide 7
02 · ROLES
Leadership & Management
Project Director
Approves logistics strategy and major resources.
Resolves escalated constraints affecting milestones, cost or stakeholders.
Ensures coordination across projects sharing resources or routes.
Project Manager
Approves the project LMP before operations commence.
Chairs or delegates the weekly logistics coordination meeting.
Reviews KPI performance, risks and unresolved corrective actions.
Logistics Manager
Develops, implements and maintains the project LMP.
Manages access routes, gates, delivery schedules and logistics zones.
Authorized to stop or reschedule any unsafe or unapproved movement.
7
Notes: At the top, three roles. The Project Director approves logistics strategy and major resources, and steps in personally when a constraint escalates that affects milestones, cost or stakeholders. The Project Manager approves the project LMP before any operation starts, chairs the weekly logistics coordination meeting — or delegates it — and reviews our KPIs, risks and open corrective actions. And the Logistics Manager is the one running it day to day: builds and maintains the LMP, manages routes, gates, schedules and zones, and — like everyone in logistics — has the authority to stop an unsafe or unapproved movement on the spot.

## Slide 8
02 · ROLES
Site Execution Team
Construction Manager
Confirms workfront readiness and material demand.
Provides construction sequencing and short-term priorities.
Nominates unloading points and responsible receiving personnel.
Logistics Supervisor
Implements the approved LMP and daily logistics programme.
Verifies bookings, permits, driver and vehicle documents.
Coordinates with Construction, Stores, HSE, Traffic and Security.
Logistics Foreman
Directs daily activities of workers, drivers and banksmen.
Runs toolbox talks and controls vehicle movement on site.
Reports damaged materials, unsafe conditions and delays immediately.
8
Notes: This is where the plan meets the ground. The Construction Manager confirms the workfront is actually ready, feeds us material demand and short-term sequencing, and nominates who receives each delivery. The Logistics Supervisor runs the daily programme, verifies every booking, permit, driver and vehicle document before anything moves, and is the main point of coordination with Stores, HSE, Traffic and Security. And the Logistics Foreman is on the ground with the crew — running toolbox talks, directing vehicle movement, and flagging damage, unsafe conditions or delays the moment they happen, not at end of shift.

## Slide 9
02 · ROLES
Support & Enabling Functions
1
Planning
Integrates logistics into the baseline schedule and rolling look-ahead.
2
Procurement & Suppliers
Aligns PO dates, confirms supplier readiness and transport arrangements.
3
Store & Warehouse
Controls receiving documentation, quarantine and rejected materials.
4
QA/QC
Defines inspection requirements and controls nonconforming materials.
5
HSE
Reviews risk assessments, JHAs, PTWs and verifies compliance.
6
Traffic Mgmt. & Engineer
Stages TMP approvals, route design and traffic-switch controls.
7
Security
Controls gate access, ID checks and vehicle authorization.
8
Interface & Stakeholder / PDIM
Coordinates authorities, utilities and cross-functional integration.
9
Notes: None of this works without support functions behind it. Planning ties logistics into the baseline schedule and the rolling look-ahead. Procurement and our suppliers align PO dates and confirm transport arrangements before we ever book a delivery. Stores and Warehouse control receiving documentation and keep rejected material quarantined and away from active stock. QA/QC defines what gets inspected and controls anything nonconforming. HSE reviews our risk assessments and permits and verifies compliance on the ground. Traffic Management and the Traffic Engineer stage TMP approvals and route design. Security controls who and what comes through the gate. And the Interface and Stakeholder team, together with the Project Delivery Integration Manager, handle authorities, utilities and cross-functional coordination. Eight functions, one team.

## Slide 10
02 · RELATIONS WITH OTHER TEAMS
Logistics Interfaces at Site
LOGISTICS
TEAM
Construction
Procurement &
Suppliers
Stores &
QA/QC
HSE &
Traffic Mgmt.
Security
Interface, Stakeholders
& Authorities
Planning
10
Notes: This is the slide I want everyone to remember: logistics doesn't operate in isolation. We sit at the center of seven relationships — Construction gives us workfront readiness and demand; Procurement and Suppliers give us what's coming and when; Stores and QA/QC control what we receive and reject; HSE and Traffic Management control how anything moves safely; Security controls who gets on site; Interface, Stakeholders and Authorities handle the external world — utilities, municipalities, permits; and Planning keeps all of it tied to the schedule. If any one of these spokes breaks down, logistics breaks down. That's why coordination isn't optional — it's the job.

## Slide 11
03
Approval Gates & Delivery Process
The control points and workflow every delivery must pass through
Notes: Next, the control points. Every delivery and every mobilization passes through a defined set of gates and a defined process — no shortcuts, no verbal approvals. Let's walk through it.

## Slide 12
03 · APPROVAL GATES
Mandatory Logistics Approval Gates
Gate 0
Contract
Activation
PD / PM
→
Gate 1
Coordination &
HSE Readiness
PM / HSE / Technical
→
Gate 2
Site Establishment
Readiness
PM / Constr. / HSE
→
Gate 3
Workfront
Release
Constr. / Log. / HSE / QA
→
Gate 4
Resources
Movement
Log. / HSE / Traffic
→
Gate 5
Demobilization
& Closeout
PM & functions
No gate may be bypassed through verbal instruction. Emergency deviations must be documented and approved by authorized management and HSE representatives.
Required Project Logistics Documents (examples)
Logistics Management Plan
Approved site layout & route plan
TMPs & traffic-switch plans
Delivery booking procedure
Logistics risk & interface register
Logistics look-ahead & KPI system
12
Notes: Six gates, from contract activation through demobilization. Gate 0 is contract activation, signed off by the PD and PM. Gate 1 checks corporate and HSE readiness. Gate 2 confirms site establishment. Gate 3 releases the workfront — that's the one Construction, Logistics, HSE and QA all sign off together. Gate 4 covers critical movements — anything abnormal or high-risk. And Gate 5 is demobilization and closeout. I want to be very clear: no gate gets bypassed with a verbal instruction, ever. If there's a genuine emergency, the deviation still gets documented and approved by authorized management and HSE — after the fact if it has to be, but it gets documented. And here are the core documents every project needs in place — the LMP, route plan, TMPs, booking procedure, interface register and KPI system.

## Slide 13
03 · DELIVERY PROCESS
Delivery Lifecycle
1
Demand
Forecasting
Construction & Planning issue rolling material and equipment demand.
→
2
Delivery
Request
PO reference, driver/vehicle details, load data and required permits.
→
3
Approval &
Scheduling
Logistics verifies workfront, route, storage and manpower availability.
→
4
Arrival, Receiving
& Closeout
Security, HSE, QA/QC and Stores clear, receive and record the delivery.
Minimum Notice Periods (proposed corporate default)
Routine delivery
≥ 72 hours
Critical concrete / asphalt
Coordinated via daily plan
Oversized / abnormal load
≥ 14 calendar days
Major crane / girder movement
≥ 14 days + lifting package
13
Notes: Every delivery follows the same four steps. It starts with demand forecasting — Construction and Planning tell us what's coming. Then a formal delivery request with PO reference, driver and vehicle details, and any permits needed. Logistics then approves and schedules it — checking the workfront, the route, storage space and manpower are actually available. And finally arrival, receiving and closeout, where Security, HSE, QA/QC and Stores all clear and record the delivery before it's considered done. Notice periods matter here — 72 hours minimum for routine deliveries, but oversized loads and major crane movements need at least 14 days. Please build that into your planning, not as an afterthought.

## Slide 14
04
Site Operations Control
Managing materials, storage, traffic and equipment day to day
Notes: Moving on to day-to-day site operations — how we manage materials and storage, and how we keep traffic, transport and internal material flow safe and unblocked.

## Slide 15
04 · SITE OPERATIONS
Material, Storage & Logistics Stations
1
Non-Inventory Materials
• Ready-mix concrete, asphalt, aggregates and backfill coordinated for direct use.
• Workfront readiness, mix approval, supplier availability confirmed before dispatch.
2
Laydown, Warehouse & Zoning
• Zoning plan covers inventory, structural steel, hazardous materials and waste.
• Rejected and quarantined materials are segregated from active stock.
3
Temporary Logistics Stations
• Detarping, concrete sampling/washout, wheel-wash and vehicle holding areas.
• Each station has approved layout, signage, lighting and inspection schedule.
15
Notes: Three areas of material control. Non-inventory materials — concrete, asphalt, aggregates, backfill — get coordinated for direct use, with mix approval and supplier availability confirmed before dispatch, since these can't sit around waiting. Laydown, warehouse and zoning covers everything from inventory and structural steel to hazardous materials and waste — with rejected and quarantined material always kept physically separate from active stock. And our temporary logistics stations — detarping, concrete sampling and washout, wheel-wash, vehicle holding — each need an approved layout, proper signage, lighting and a regular inspection schedule. These aren't informal areas; they're controlled stations.

## Slide 16
04 · SITE OPERATIONS
Traffic, Heavy Transport & Internal Flow
1
Traffic, Access & Route Management
No movement affecting live traffic proceeds until Traffic Management confirms controls: segregated routes, marshals, barriers, signage and continuous emergency access.
2
Heavy Transport, Cranes & Equipment
Mobilized per the approved histogram. Route geometry, ground bearing capacity, permits, lifting plan, JHA and PTW verified before movement.
3
Internal Material Flow
Movement from stores/laydown to workfronts is controlled by an approved issue or transfer request, minimizing double handling and blocked access.
16
Notes: Three more controls that keep the site moving safely. Traffic, access and route management — nothing that touches live traffic moves until Traffic Management confirms segregated routes, marshals, barriers, signage and, critically, that emergency access stays open at all times. Heavy transport, cranes and equipment mobilize strictly per the approved histogram, with route geometry, ground bearing capacity, permits, the lifting plan, JHA and PTW all verified before anything moves. And internal material flow — from stores or laydown to the workfront — always goes through an approved issue or transfer request. That's how we cut down on double handling and keep access routes from getting blocked.

## Slide 17
05
Communication, KPIs & Escalation
How the team stays aligned and how performance is measured
Notes: Now let's talk about how we stay aligned as a team, and how we measure whether logistics is actually performing — our meeting cadence, the interface register, and our KPIs.

## Slide 18
05 · COMMUNICATION
Communication Structure & Interface Register
Meeting Cadence
Daily
Logistics coordination meeting & delivery/equipment schedule
Weekly
Logistics look-ahead + interface and permit review
Monthly
Management performance review
As needed
Advance coordination for critical lifts or abnormal loads
Logistics Interface Register — Status Rules
Green
No effect on the approved sequence.
Amber
Potential effect — recovery action required.
Red
Milestone, safety, authority or traffic impact — immediate escalation.
Register fields: issue & location · affected activity/milestone · responsible party · required decision · target closure date · status · escalation level.
18
Notes: Alignment happens through a fixed meeting cadence — daily coordination on deliveries and equipment, a weekly look-ahead plus interface and permit review, and a monthly management review. Anything critical, like a major lift, gets extra advance coordination on top of that. And this is how we track issues: the Logistics Interface Register uses a simple traffic-light system. Green means no effect on the approved sequence — just log it. Amber means there's a potential effect and it needs a recovery action. Red means it's hitting a milestone, safety, an authority, or traffic — and that gets escalated immediately, not at the next scheduled meeting. Every entry in the register carries a responsible party and a target closure date, so nothing just sits open indefinitely.

## Slide 19
05 · MONITORING
Key Performance Indicators
≥95%
Deliveries completed
within approved slot
100%
Pre-arrival documentation
complete
100%
TMP & access-route
inspections completed
≥90%
Corrective actions
closed within target
Zero
Preventable material
damage events
Zero
Unauthorized
gate entries
19
Notes: This is how we know if logistics is actually performing, not just busy. Ninety-five percent or more of deliveries land within their approved slot. A hundred percent of pre-arrival documentation complete — no partial paperwork. A hundred percent of TMP and access-route inspections completed on schedule. Ninety percent or more of corrective actions closed within their target date. And two numbers that should always read zero: preventable material damage, and unauthorized gate entries. These go into the monthly management review, and if any of them start slipping, that's our early warning sign — we act on it immediately, not at project closeout.

## Slide 20
06
Risk, Nonconformance & Closeout
Staying ahead of disruption and closing the project out cleanly
Notes: Last section: how we stay ahead of risk, how we handle it when something goes wrong, and how we close a project out properly instead of leaving loose ends.

## Slide 21
06 · CONTROL
Risk & Nonconformance Management
Top Logistics Risks
Delivery delays & supplier failure
Access or route restrictions
Traffic congestion & lane reductions
Utility conflicts & workfront readiness
Equipment or crane-access conflicts
Weather, dust and visibility
Controls: alternative suppliers, backup routes, buffer stock, off-peak delivery, standby lifting equipment, early authority engagement.
Nonconformance Handling
Record
Assign
Risk-rate
Correct
Verify
Close
Repeated or serious nonconformities are escalated to the Project Manager and HSE Manager and may result in suspension of the supplier or transporter.
Typical nonconformities
• Unauthorized or unbooked delivery
• Use of an unapproved route
• Missing permit, certificate or inspection
• Blocked emergency or public access
21
Notes: On the left, the risks we watch for most — delivery delays, route restrictions, congestion, utility conflicts, equipment clashes, weather. We manage those with alternative suppliers, backup routes, buffer stock and early engagement with authorities, not by hoping they don't happen. On the right, how we handle it when something actually goes wrong: record it, assign an owner, risk-rate it, correct it, verify the fix, and only then close it. Six steps, always in that order. If a nonconformity repeats or is serious — an unauthorized delivery, an unapproved route, a missing permit, blocked emergency access — it goes straight to the Project Manager and HSE Manager, and yes, that can mean suspending a supplier or transporter.

## Slide 22
06 · CLOSEOUT
Demobilization, Handover & Our Commitment
Removal of temporary facilities, stations and utilities.
Equipment, vehicle and asset demobilization and reconciliation.
Reinstatement of temporary diversions and laydown areas.
Permit and authority closeout, record handover and archive.
Lessons-learned workshop and closeout report.
No logistics area is handed over until it is inspected, cleared, reinstated and formally accepted.
“
MAH manages logistics as an integrated project-control function — not merely a transportation service.
Successful logistics requires coordinated planning between Procurement, Stores, Construction, Planning, HSE, QA/QC, Traffic Management, Security, Interface Management, suppliers and subcontractors.
22
Notes: Closeout matters as much as the setup did. We remove temporary facilities and stations, reconcile every piece of equipment and asset, reinstate anything we diverted or occupied, close out permits with the authorities, and archive the records. We run a lessons-learned workshop before we walk away — not after we've already forgotten what happened. And the rule is simple: no logistics area gets handed over until it's inspected, cleared, reinstated and formally accepted — no exceptions. Which brings me to the point I want to leave you with: logistics here isn't just moving trucks around. It's an integrated project-control function, and it only works when Procurement, Stores, Construction, Planning, HSE, QA/QC, Traffic, Security and Interface Management are all pulling in the same direction. That's what today was about. Thank you.

## Slide 23
Thank You
Questions & Discussion
Notes: That's the full procedure. Open floor now — questions on any role, any gate, any interface we covered. If something wasn't clear or you think a step is missing for your specific project, raise it now so we can fold it into the project-specific LMP rather than finding out on site.